## Example
Project Controls NextGen · Critical Path Method worksheet (weeks, finish-to-start)
Power Infrastructure Upgrade. Fictional training data. Not a real project, utility or company.
ID | Activity | Duration | Predecessors | ES | EF | LS | LF | TF | FF | Critical?
A | Kickoff and permits | 8 |  | 0 | 8 | 0 | 8 | 0 | 0 | Yes
B | Detailed engineering | 20 | A | 8 | 28 | 8 | 28 | 0 | 0 | Yes
C | Procure power transformers (long lead) | 52 | B | 28 | 80 | 28 | 80 | 0 | 0 | Yes
D | Site preparation and civil | 16 | A | 8 | 24 | 36 | 52 | 28 | 0
E | Substation foundations | 12 | D | 24 | 36 | 52 | 64 | 28 | 22
G | Procure switchgear | 30 | B | 28 | 58 | 34 | 64 | 6 | 0
F | Steel and switchgear install | 16 | E, G | 58 | 74 | 64 | 80 | 6 | 6
H | Transformer installation | 8 | C, F | 80 | 88 | 80 | 88 | 0 | 0 | Yes
I | Transmission line upgrade | 40 | B | 28 | 68 | 48 | 88 | 20 | 20
J | Line tie-in | 4 | I, H | 88 | 92 | 88 | 92 | 0 | 0 | Yes
K | Testing and commissioning | 10 | J | 92 | 102 | 92 | 102 | 0 | 0 | Yes
L | Energization and handover | 2 | K | 102 | 104 | 102 | 104 | 0 | 0 | Yes
| Project finish (latest EF) |  |  |  | 104

## Your network
Project Controls NextGen · CPM worksheet
Enter activities, durations and predecessors. Type ES and LF yourself using the rules on 'How to use'; the other columns calculate.
ID | Activity | Duration | Predecessors | ES | EF | LS | LF | TF | FF | Critical?

## How to use
Critical Path Method worksheet
Forward pass (top to bottom): ES = the latest EF of all predecessors (0 for start activities). EF = ES + duration.
Project finish = the latest EF in the network.
Backward pass (bottom to top): LF = the earliest LS of all successors (the project finish for end activities). LS = LF − duration.
Total float (TF) = LS − ES. Free float (FF) = earliest ES of successors − EF. Activities with TF = 0 are on the critical path.
The Example sheet solves the fictional Power Infrastructure Upgrade network from the simulator: 104 weeks, critical path A-B-C-H-J-K-L.